## Project Timeline
Project InterpretAir Timeline
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
| Date | Milestone | Assigned To | Position | Baseline
| 2018-01-22 | Project Start |  | 20 | 0
| 2018-02-13 | Project Blueprint | Team | 10 | 0
| 2018-02-20 | Understand the APIs and services | Developer | -10 | 0
| 2018-02-27 | Intergrate all compoments |  | 25 | 0
| 2018-03-04 | Continuous Intergration | IT Operation | -15 | 0
| 2018-03-12 | Midterm All components in place | Team | 15 | 0
| 2018-03-26 | Authentication | Developer | 15 | 0
| 2018-04-02 | UI Finished | UIUX Developer | -20 | 0
| 2018-04-16 | Packer & Vagrant | IT Operation | -15 | 0
| 2018-04-23 | Final Report | Team | 10 | 0
| 2018-04-30 | Project End |  | 20 | 0